## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
Hybrid Model Performance: The dual-backbone fusion of EfficientNetB3 and DenseNet121 was highly successful, achieving a test accuracy of 95.5%. The strategy of concatenating embeddings allowed the model to capture both scalable features and dense connectivity patterns effectively. | Class Overlap (TB & Pneumonia): While overall accuracy is high, the t-SNE visualization revealed a significant overlap between Tuberculosis and Pneumonia clusters. This reflects clinical realities but poses a risk for misclassification in a live diagnostic setting. | Explainability Integration: We should incorporate Grad-CAM or similar heat-mapping techniques. This would allow clinicians to see exactly which regions of the lung the model is highlighting when it makes a "TB" vs "Pneumonia" call. | "We need to prioritize the integration of a visualization layer. Let’s start by testing the Grad-CAM library on the existing model to see if the heatmaps align with known clinical markers for TB. This will help us build trust in the model's decision-making process."
Data Pipeline Stability: The preprocessing workflow involving normalization and resizing handled the 13,209 images without memory overflows. The use of class weights effectively mitigated the residual imbalance in the dataset. | Inference Latency on CPU: While the model performs exceptionally well on a GPU, the dual-backbone architecture is computationally heavy. Initial tests suggest inference times might be too slow for low-resource environments lacking high-end hardware. | Model Quantization: To make the system deployable in real-world clinics, we could explore Post-Training Quantization (PTQ) or converting the model to TensorFlow Lite to reduce its size and increase speed without sacrificing too much accuracy. | "Let's look into optimizing the model for edge devices. We should run a series of benchmarks on standard CPU environments and then apply quantization. If we can get the inference time under 100ms on a standard laptop, it’s a huge win for clinical accessibility."
Class Separation (COVID vs Normal): The model showed near-perfect separation between COVID-19 and Normal cases in the latent space. This confirms the robustness of the feature extraction for distinct radiographic signatures. | Dataset Diversity: The current performance is grounded in a specific dataset split. There is a lack of "out-of-distribution" testing, meaning the model might struggle with X-ray images from different machines or hospitals with varying contrast settings. | External Clinical Validation: The next phase should involve testing the model on completely unseen data from local hospitals or different public repositories to ensure it isn't "over-fitting" to the specific characteristics of the current dataset. | "It’s time to move beyond the current dataset. We should reach out to partner institutions or find a secondary dataset to run a blind test. If the accuracy holds up there, we can confidently move toward the microservices architecture mentioned in our roadmap."
Training Efficiency: The use of AdamW and EarlyStopping worked perfectly. The training stabilized around 96% accuracy without significant divergence, saving hours of unnecessary compute time. | Pneumonia Feature Heterogeneity: Pneumonia showed the widest spread in the t-SNE plot, indicating that the model is struggling to find a "uniform" signature for the various types of pneumonia included in the data. | Sub-class Classification: We could look into breaking the Pneumonia class down further (e.g., Viral vs Bacterial) if the data allows. This might actually help the model distinguish it more clearly from TB. | "Let’s do a deep dive into the Pneumonia false negatives. If we can identify whether the errors are concentrated in viral or bacterial cases, we can adjust our training weights or data augmentation specifically for those subsets to sharpen the boundaries."